## 开机问题跟踪表
状态 | 优先级 | 类别 | 问题描述 | 进展 | 当前责任人 | 提出日期 | 计划完成日期 | 解决方案 | 经验总结 | 发生问题的CPB版本 | 备注 | 日志
修改验证中 | 3.中 | 性能 | 使用bootgraph工具，需要将initcall_debugprintk.time=1 |  | 张杰 | 2015-07-14 | 2015-07-15
修改验证中 | 3.中 | 性能 | 启动分阶段耗时日志统计 |  | 张杰 | 2015-07-14 | 2015-07-15
open | 3.中 | 性能 | Package Scanning优化外部迭代器 | 7.14：等孙宁回复确认CR：865522 | 陈涌 | 2015-07-14 | 2015-07-15
open | 3.中 | 性能 | 使用多任务方式提升package scan时间 | 7.14：等孙宁回复确认CR：859683 | 陈涌 | 2015-07-14 | 2015-07-15 | 可以通过配置persist.pm.multitask来优化启动时间
open | 3.中 | 性能 | SMB1360驱动优化 | 7.14：等孙宁回复确认CR：829505 | 李海波 | 2015-07-14 | 2015-07-15 | 手机重启或者时，SMB1360驱动初始化会有明显的延迟 | 将耗时部分放到worker thread
open | 3.中 | 性能 | 内核编译配置选项 | 确保使用perf_defconfig来编译kernel | 李海波 | 2015-07-14 | 2015-07-15
closed | 3.中 | 性能 | Relocate GC duringzygote initialization | 7.14:共有三个地方，底版本已合入两个 | 陈涌 | 2015-07-14 | 2015-07-15 | https://www.codeaurora.org/cgit/quic/la//platform/frameworks/base/commit/?id=fbc95831d2e4d5f089605c1622c25dee91154b39
open | 3.中 | 性能 | Serial-console and early printkremoved |  | 李海波 | 2015-07-14 | 2015-07-15 | https://www.codeaurora.org/cgit/quic/la//kernel/msm-3.10/commit/?id=3a008678674a38f47f2fe32f4137cc7795b05b08https://www.codeaurora.org/cgit/quic/la//platform/vendor/qcom/plutonium/commit/?id=92040a58272fea1111251f5f42115b244d94df64 |  |  | diff --git a/arch/arm64/configs/msm8994-perf_defconfig b/arch/arm64/configs/msm8994-perf_defconfig index 76b605c..7887bbd 100644 --- a/arch/arm64/configs/msm8994-perf_defconfig +++ b/arch/arm64/configs/msm8994-perf_defconfig @@ -269,8 +269,6 @@ CONFIG_INPUT_GPIO=m # CONFIG_SERIO_I8042 is not set # CONFIG_VT is not set CONFIG_SERIAL_MSM_HS=y -CONFIG_SERIAL_MSM_HSL=y -CONFIG_SERIAL_MSM_HSL_CONSOLE=y CONFIG_SERIAL_MSM_SMD=y CONFIG_DIAG_CHAR=y CONFIG_HW_RANDOM=y
closed | 3.中 | 性能 | Enable 2 A57’s inthe boot cmdlineparms | 7.14：已有加 | 陈涌 | 2015-07-14 | 2015-07-15 | https://www.codeaurora.org/cgit/quic/la//platform/vendor/qcom/plutonium/commit/?id=7b7930dfe16245d587a7e2909efa860aa0c1a191 |  |  |  | diff --git a/BoardConfig.mk b/BoardConfig.mk index aca84f3..02c228e 100644 --- a/BoardConfig.mk +++ b/BoardConfig.mk @@ -48,7 +48,7 @@ TARGET_USES_ION := true TARGET_USES_NEW_ION_API :=true TARGET_USES_OVERLAY := true -BOARD_KERNEL_CMDLINE := console=ttyHSL0,115200,n8 androidboot.console=ttyHSL0 androidboot.hardware=qcom user_debug=31 msm_rtb.filter=0x37 ehci-hcd.park=3 lpm_levels.sleep_disabled=1 boot_cpus=0-3 +BOARD_KERNEL_CMDLINE := console=ttyHSL0,115200,n8 androidboot.console=ttyHSL0 androidboot.hardware=qcom user_debug=31 msm_rtb.filter=0x37 ehci-hcd.park=3 lpm_levels.sleep_disabled=1 boot_cpus=0-5 BOARD_EGL_CFG := device/qcom/$(TARGET_BOARD_PLATFORM)/egl.cfg BOARD_KERNEL_SEPARATED_DT := true
closed | 3.中 | 性能 | 启动时CPU配置 Apply Sched-boost during boot (Userspaceonly) | 7.14：已有加 | 陈涌 | 2015-07-14 | 2015-07-15 | https://www.codeaurora.org/cgit/quic/la//platform/vendor/qcom/plutonium/commit/?id=8de0e5dbd520c816b3b6ce7da8205257b6d99242https://www.codeaurora.org/cgit/quic/la//device/qcom/common/commit/?id=90d812f2c7d24e4a3cab8ab111cafabc58d690d8 |  |  |  | diff --git a/init.target.rc b/init.target.rc index 488c872..38760fc 100644 --- a/init.target.rc +++ b/init.target.rc @@ -63,6 +63,7 @@ on boot start rmt_storage start rfs_access write /sys/bus/i2c/devices/2-0020/input/input0/update_fw 1 + write /proc/sys/kernel/sched_boost 1 diff --git a/rootdir/etc/init.qcom.post_boot.sh b/rootdir/etc/init.qcom.post_boot.sh index fdac151..579a863 100644 --- a/rootdir/etc/init.qcom.post_boot.sh +++ b/rootdir/etc/init.qcom.post_boot.sh @@ -832,6 +832,7 @@ case "$target" in echo 85 > /proc/sys/kernel/sched_downmigrate echo 400000 > /proc/sys/kernel/sched_freq_inc_notify echo 400000 > /proc/sys/kernel/sched_freq_dec_notify + echo 0 > /proc/sys/kernel/sched_boost #enable rps static configuration echo 8 > /sys/class/net/rmnet_ipa0/queues/rx-0/rps_cpus for devfreq_gov in /sys/class/devfreq/qcom,cpubw*/governor
open | 3.中 | 性能 | Skip SELinuxlabelling for BCL nodeshttps | 7.14：等孙宁回复确认 | 陈涌 | 2015-07-14 | 2015-07-15 | https://www.codeaurora.org/cgit/quic/la//device/qcom/sepolicy/commit/?id=ef79aaa04b8bdd68bc700ed2fd5885e0334ecfef |  |  |  | diff --git a/common/file_contexts b/common/file_contexts index 24d88e8..98fff32 100644 --- a/common/file_contexts +++ b/common/file_contexts @@ -183,7 +183,6 @@ # /sys/class/graphics/fb0/mdp/caps u:object_r:sysfs_graphics:s0 /sys/class/thermal(/.*)? u:object_r:sysfs_thermal:s0 -/sys/devices/.*bcl.*(/.*)? u:object_r:sysfs_thermal:s0 /sys/devices/f9200000.*/power_supply/usb(/.*)? u:object_r:sysfs_usb_supply:s0 /sys/devices/msm_dwc3/power_supply/usb(/.*)? u:object_r:sysfs_usb_supply:s0 /sys/devices/msm_otg/power_supply/usb(/.*)? u:object_r:sysfs_usb_supply:s0 现我们版本是如下三句 /sys/class/graphics/fb0/mdp/caps u:object_r:sysfs_graphics:s0 /sys/class/thermal(/.*)? u:object_r:sysfs_thermal:s0 /sys/devices/soc.0/qcom,bcl.*(/.*)? u:object_r:sysfs_thermal:s0 /sys/devices/qcom,bcl.*(/.*)? u:object_r:sysfs_thermal:s0
open | 3.中 | 性能 | Move qpnp-fgtasks (updating SRAM)to worker thread Read eepromdata during daemon initialization rather than at boot timehttps://www.codeaurora.org/cgit/quic/la//kernel/msm- |  | 李海波 | 2015-07-14 | 2015-07-15 | https://www.codeaurora.org/cgit/quic/la//kernel/msm-3.10/commit/?id=c4301419358485fa265df9c1adac9ec1a600418chttps://www.codeaurora.org/cgit/quic/la//kernel/msm-3.10/commit/?id=5f0ca02b07d8f986115009af23c86c2c617961fa
open | 3.中 | 性能 | Read eepromdata during daemon initialization rather than at boot timehttps |  | 王强 | 2015-07-14 | 2015-07-15 | https://www.codeaurora.org/cgit/quic/la/kernel/msm-3.10/commit/?id=5f0ca02b07d8f986115009af23c86c2c617961fa
open | 3.中 | 性能 | Fix bootanimationexit delay 5s when device muted | 7.14：等孙宁回复确认 | 陈涌 | 2015-07-14 | 2015-07-16
closed | 3.中 | 性能 | zygote: change zygote class type from main to core for boot time | 7.14：已修改到DEBUG流验证 | 陈涌 | 2015-07-14 | 2015-07-15
Note on A3: 作者: 需按照问题的现状来更新状态。 需要重现的问题要在三天内进行更进复现； close的问题需要在后面加上关闭的日期；
Note on D3: 作者: 写明标题、描述和概率，以便后续能清晰的核对问题。
Note on E3: 作者: 最新更新内容需置顶。
Note on B4: 作者: 下拉框
Note on B5: 作者: 下拉框
Note on B6: 作者: 下拉框
Note on B7: 作者: 下拉框
Note on B8: 作者: 下拉框
Note on B9: 作者: 下拉框
Note on B10: 作者: 下拉框
Note on B11: 作者: 下拉框
Note on B12: 作者: 下拉框
Note on B13: 作者: 下拉框
Note on B14: 作者: 下拉框
Note on B15: 作者: 下拉框
Note on B16: 作者: 下拉框
Note on B17: 作者: 下拉框
Note on B18: 作者: 下拉框

## 开机优化表
CP8692 3GB RAM
阶段结点 | 8692(CP8692_5.1_V011_2015.06.22-11.10) |  |  | 日志类别 | 8691 |  |  | 日志类别
| 耗时 | 时间戳 | 日志 |  | 耗时 | 时间戳 | 日志
bootloader的耗时
内核启动 | -4438 | 45971 | <6>[ 0.000000]@0 | kmsg | -5125 | 42489 | <6>[ 0.000000]@0 Booting Linux on physical CPU 0 | kmsg
init进程启动开始 | -2447 | 47962 | <6>[ 1.991625]@4 Freeing unused kernel memory: 80K (ffffffc001400000 - ffffffc001414000) | kmsg | -2786 | 44828 | <6>[ 2.339660]@0 Freeing init memory: 56K | kmsg
SurfaceFlinger开始 | 0 | 50409 | 01-01 14:14:50.409 I/SurfaceFlinger( 372): SurfaceFlinger is starting | main | 0 | 47614 | 03-10 08:20:44.600 I/SurfaceFlinger( 357): SurfaceFlinger is starting | main
AndroidRuntime启动 | 530 | 50939 | 05-28 14:14:50.939 I/boot_progress_start( 479): 4968 | events | 440 | 48054 | 03-10 08:20:45.040 I/boot_progress_start( 358): 5565 | events
预加载开始 | 1180 | 51589 | 05-28 14:14:51.589 I/boot_progress_preload_start( 480): 5610 | events | 1044 | 48658 | 04-22 09:09:48.658 I/boot_progress_preload_start( 358): 6169 | events
预加载结束 | 3560 | 53969 | 05-28 14:14:53.969 I/boot_progress_preload_end( 480): 7993 | events | 5694 | 53308 | 04-22 09:09:53.308 I/boot_progress_preload_end( 358): 10816 | events
SystemServer进程开始 | 4030 | 54439 | 05-28 14:14:54.439 I/boot_progress_system_run( 1042): 8464 | events | 5954 | 53568 | 04-22 09:09:53.568 I/boot_progress_system_run( 976): 11077 | events
PMS开始运行 | 7120 | 57529 | 05-28 14:14:57.529 I/boot_progress_pms_start( 1042): 11559 | events | 6104 | 53718 | 04-22 09:09:53.718 I/boot_progress_pms_start( 976): 11221 | events
PMS开始扫描system分区文件数据 | 7220 | 57629 | 05-28 14:14:57.629 I/boot_progress_pms_system_scan_start( 1042): 11656 | events | 6334 | 53948 | 04-22 09:09:53.948 I/boot_progress_pms_system_scan_start( 976): 11459 | events
PMS开始扫描data分区文件数据 | 12380 | 62789 | 05-28 14:15:02.789 I/boot_progress_pms_data_scan_start( 1042): 16811 | events | 10213 | 57827 | 04-22 09:09:57.827 I/boot_progress_pms_data_scan_start( 976): 15338 | events
PMS扫描结束 | 12380 | 62789 | 05-28 14:15:02.789 I/boot_progress_pms_scan_end( 1042): 16817 | events | 10283 | 57897 | 04-22 09:09:57.897 I/boot_progress_pms_scan_end( 976): 15404 | events
PMS ready状态开始 | 12410 | 62819 | 05-28 14:15:02.819 I/boot_progress_pms_ready( 1042): 16843 | events | 10403 | 58017 | 04-22 09:09:58.017 I/boot_progress_pms_ready( 976): 15529 | events
AMS ready状态开始 | 29440 | 79849 | 05-28 14:15:19.849 I/boot_progress_ams_ready( 1042): 33870 | events | 11403 | 59017 | 04-22 09:09:59.017 I/boot_progress_ams_ready( 976): 16525 | events
phone启动 | 29480 | 79889 | 05-28 14:15:19.889 I/am_proc_start( 1042): [0,4057,1001,com.android.phone,added application,com.android.phone] | events | 11423 | 59037 | 04-22 09:09:59.037 I/am_proc_start( 976): [0,1208,1001,com.android.phone,added application,com.android.phone,16547] | events
systemui启动 | 29660 | 80069 | 05-28 14:15:20.069 I/am_proc_start( 1042): [0,4137,10012,com.android.systemui,service,com.android.systemui/.SystemUIService] | events | 11433 | 59047 | 04-22 09:09:59.047 I/am_proc_start( 976): [0,1223,1000,com.android.systemui,service,com.android.systemui/.SystemUIService,16559] | events
usbui启动 | 29700 | 80109 | 05-28 14:15:20.109 I/am_proc_start( 1042): [0,4160,1000,com.android.usbui,service,com.android.usbui/.UsbUIService] | events | 11453 | 59067 | 04-22 09:09:59.067 I/am_proc_start( 976): [0,1240,1000,com.android.usbui,service,com.android.usbui/.UsbUIService,16570] | events
keyguard启动 | 33470 | 83879 | 05-28 14:15:23.879 I/am_proc_start( 1042): [0,4838,10012,com.android.systemui,service,com.android.systemui/.keyguard.KeyguardService] | events | 11353 | 58967 | 04-22 09:09:58.967 I/am_proc_start( 976): [0,1193,10020,com.android.keyguard,service,com.android.keyguard/.KeyguardService,16471] | events
launcher启动 | 33570 | 83979 | 05-28 14:15:23.979 I/am_proc_start( 1042): [0,4903,10037,com.yulong.android.launcher3,activity,com.yulong.android.launcher3/.Launcher] | events | 12343 | 59957 | 04-22 09:09:59.957 I/am_proc_start( 976): [0,1505,10055,com.yulong.android.launcher3,activity,com.yulong.android.launcher3/.Launcher,17466] | events
AMS 启动完成 | 30330 | 80739 | 05-28 14:15:20.739 I/boot_progress_enable_screen( 1042): 34766 | events | 12993 | 60607 | 04-22 09:10:00.607 I/boot_progress_enable_screen( 976): 18112 | events
SurfaceFlinger关动画出keygurad | 38750 | 89159 | 05-28 14:15:29.159 I/SurfaceFlinger( 372): Boot is finished (39312 ms) | main | 21043 | 68657 | 04-22 09:10:08.657 I/SurfaceFlinger( 357): Boot is finished (21039 ms) | main
总耗时 | 43188 |  |  |  | 26168
内核系统日志同一时间点对标 |  |  | <6>[ 1.959181]@4 qcom,qpnp-rtc qpnp-rtc-ffffffc0c569d000: setting system clock to 2015-05-28 06:14:48 UTC (22488) | kmsg |  |  | <6>[ 2.019649]@0 qcom,qpnp-rtc qpnp-rtc-e8cf9200: setting system clock to 1970-03-10 00:20:41 UTC (5876441) | kmsg
阶段结点 | 8692(CP8692_5.1_V011_2015.06.22-11.10) |  |  | 日志类别 | T2 |  |  | 日志类别
| 耗时 | 时间戳 | 日志 |  | 耗时 | 时间戳 | 日志
bootloader的耗时
内核启动 | -4605 | 44814 | <6>[ 0.000000]@0 | kmsg | -3978 | 27151 | <6>[ 0.000000]@0 | kmsg
init进程启动开始 | -2680 | 46739 | <6>[ 1.925535]@5 Freeing unused kernel memory: 80K (ffffffc001400000 - ffffffc001414000) | kmsg | -2228 | 28901 | <6>[ 1.750971] Freeing unused kernel memory: 416K (ffffffc000e48000 - ffffffc000eb0000) | kmsg
SurfaceFlinger开始 | 0 | 49419 | 01-01 11:20:49.419 I/SurfaceFlinger( 361): SurfaceFlinger is starting | main | 0 | 31129 | 01-02 20:06:31.129 I/SurfaceFlinger( 307): SurfaceFlinger is starting | main
AndroidRuntime启动 | 180 | 49599 | 05-28 11:20:49.599 I/boot_progress_start( 489): 4788 | events | 1810 | 32939 | 01-02 20:06:32.939 I/boot_progress_start( 411): 5788 | events
预加载开始 | 960 | 50379 | 05-28 11:20:50.379 I/boot_progress_preload_start( 490): 5565 | events | 3510 | 34639 | 01-02 20:06:34.639 I/boot_progress_preload_start( 411): 7488 | events
预加载结束 | 2930 | 52349 | 05-28 11:20:52.349 I/boot_progress_preload_end( 490): 7536 | events | 6260 | 37389 | 01-02 20:06:37.389 I/boot_progress_preload_end( 413): 10238 | events
SystemServer进程开始 | 3070 | 52489 | 05-28 11:20:52.489 I/boot_progress_system_run( 1144): 7674 | events | 6570 | 37699 | 01-02 20:06:37.699 I/boot_progress_system_run( 930): 10543 | events
PMS开始运行 | 3310 | 52729 | 05-28 11:20:52.729 I/boot_progress_pms_start( 1144): 7916 | events | 6940 | 38069 | 01-02 20:06:38.069 I/boot_progress_pms_start( 930): 10918 | events
PMS开始扫描system分区文件数据 | 3390 | 52809 | 05-28 11:20:52.809 I/boot_progress_pms_system_scan_start( 1144): 7992 | events | 7110 | 38239 | 01-02 20:06:38.239 I/boot_progress_pms_system_scan_start( 930): 11084 | events
PMS开始扫描data分区文件数据 | 8210 | 57629 | 05-28 11:20:57.629 I/boot_progress_pms_data_scan_start( 1144): 12811 | events | 16040 | 47169 | 01-02 20:06:47.169 I/boot_progress_pms_data_scan_start( 930): 20013 | events
PMS扫描结束 | 8230 | 57649 | 05-28 11:20:57.649 I/boot_progress_pms_scan_end( 1144): 12838 | events | 16490 | 47619 | 01-02 20:06:47.619 I/boot_progress_pms_scan_end( 930): 20464 | events
PMS ready状态开始 | 8270 | 57689 | 05-28 11:20:57.689 I/boot_progress_pms_ready( 1144): 12876 | events | 16620 | 47749 | 01-02 20:06:47.749 I/boot_progress_pms_ready( 930): 20592 | events
AMS ready状态开始 | 9890 | 59309 | 05-28 11:20:59.309 I/boot_progress_ams_ready( 1144): 14490 | events | 18660 | 49789 | 01-02 20:06:49.789 I/boot_progress_ams_ready( 930): 22637 | events
phone启动 | 9960 | 59379 | 05-28 11:20:59.379 I/am_proc_start( 1144): [0,3538,1001,com.android.phone,added application,com.android.phone] | events | 18760 | 49889 | 01-02 20:06:49.889 I/am_proc_start( 930): [0,1253,1001,com.android.phone,added application,com.android.phone] | events
systemui启动 | 10070 | 59489 | 05-28 11:20:59.489 I/am_proc_start( 1144): [0,3619,10013,com.android.systemui,service,com.android.systemui/.SystemUIService] | events | 18610 | 49739 | 01-02 20:06:49.739 I/am_proc_start( 930): [0,1199,10079,com.android.systemui,service,com.android.systemui/.keyguard.KeyguardService] | events
usbui启动 | 10110 | 59529 | 05-28 11:20:59.529 I/am_proc_start( 1144): [0,3642,1000,com.android.usbui,service,com.android.usbui/.UsbUIService] | events | 18970 | 50099 | 01-02 20:06:50.099 I/am_proc_start( 930): [0,1330,1000,com.android.usbui,service,com.android.usbui/.UsbUIService] | events
keyguard启动 | 10070 | 59489 | 05-28 11:20:59.489 I/am_proc_start( 1144): [0,3619,10013,com.android.systemui,service,com.android.systemui/.SystemUIService] | events | 18610 | 49739 | 01-02 20:06:49.739 I/am_proc_start( 930): [0,1199,10079,com.android.systemui,service,com.android.systemui/.keyguard.KeyguardService] | events
launcher启动 | 10900 | 60319 | 05-28 11:21:00.319 I/am_proc_start( 1144): [0,4163,10037,com.yulong.android.launcher3,activity,com.yulong.android.launcher3/.Launcher] | events | 20570 | 51699 | 01-02 20:06:51.699 I/am_proc_start( 930): [0,1881,10043,com.yulong.android.launcher3,activity,com.yulong.android.launcher3/.Launcher] | events
AMS 启动完成 | 11230 | 60649 | 05-28 11:21:00.649 I/boot_progress_enable_screen( 1144): 15832 | events | 22420 | 53549 | 01-02 20:06:53.549 I/boot_progress_enable_screen( 930): 26392 | events
SurfaceFlinger关动画出keygurad | 9190 | 58609 | 05-28 11:20:58.609 I/SurfaceFlinger( 361): Boot is finished (10004 ms) | main | 25560 | 56689 | 01-02 20:06:56.689 I/SurfaceFlinger( 307): Boot is finished (25184 ms) | main
总耗时 | 13795 |  |  |  | 29538
内核系统日志同一时间点对标 |  |  | <6>[ 1.895988]@5 qcom,qpnp-rtc qpnp-rtc-ffffffc0c5660800: setting system clock to 2015-05-28 03:20:47 UTC (12047) | kmsg |  |  | <6>[ 1.703436] qcom,qpnp-rtc qpnp-rtc-ffffffc073cd3c00: setting system clock to 1970-01-02 12:06:28 UTC (129988) | kmsg
阶段结点 | 8692(CP8692_5.1_V020_2015.07.21-21.41) |  |  | 日志类别 | 8692(CP8692_5.1_V33)
| 耗时 | 时间戳 | 日志 |  | 耗时 | 时间戳 | 日志
bootloader的耗时
内核启动 | -3739 | 30580 | <6>[ 0.000000]@4 Initializing cgroup subsys cpu | kmsg | -4274 | 37467 | 0<6>[ 0.000000]@5 Initializing cgroup subsys cpu
init进程启动开始 | -1796 | 32523 | <6>[ 1.942946]@4 Freeing unused kernel memory: 80K (ffffffc001400000 - ffffffc001414000) | kmsg | -2504 | 39237 | <6>[ 1.770823]@0 Freeing unused kernel memory: 80K (ffffffc001400000 - ffffffc001414000)
SurfaceFlinger开始 | 0 | 34319 | 07-02 07:45:34.319 I/SurfaceFlinger( 359): SurfaceFlinger is starting | main | 0 | 41741 | 07-06 05:00:59.529 I/SurfaceFlinger( 360): SurfaceFlinger is starting
AndroidRuntime启动 | 350 | 34669 | 07-02 07:45:34.669 I/boot_progress_start( 370): 4089 | events | 187 | 41928 | 08-14 16:47:41.928 I/boot_progress_start( 372): 4461
预加载开始 | 1560 | 35879 | 07-02 07:45:35.879 I/boot_progress_preload_start( 370): 5297 | events | 1107 | 42848 | 08-14 16:47:42.848 I/boot_progress_preload_start( 372): 5380
预加载结束 | 3150 | 37469 | 07-02 07:45:37.469 I/boot_progress_preload_end( 372): 6888 | events | 2727 | 44468 | 08-14 16:47:44.468 I/boot_progress_preload_end( 373): 7001
SystemServer进程开始 | 3300 | 37619 | 07-02 07:45:37.619 I/boot_progress_system_run( 1150): 7039 | events | 2857 | 44598 | 08-14 16:47:44.598 I/boot_progress_system_run( 1159): 7136
PMS开始运行 | 3580 | 37899 | 07-02 07:45:37.899 I/boot_progress_pms_start( 1150): 7312 | events | 3097 | 44838 | 08-14 16:47:44.838 I/boot_progress_pms_start( 1159): 7379
PMS开始扫描system分区文件数据 | 3670 | 37989 | 07-02 07:45:37.989 I/boot_progress_pms_system_scan_start( 1150): 7408 | events | 2877 | 44618 | 08-14 16:47:44.918 I/boot_progress_pms_system_scan_start( 1159): 7459
PMS开始扫描data分区文件数据 | 8600 | 42919 | 07-02 07:45:42.919 I/boot_progress_pms_data_scan_start( 1150): 12333 | events | 8717 | 50458 | 08-14 16:47:50.458 I/boot_progress_pms_data_scan_start( 1159): 12994
PMS扫描结束 | 8600 | 42919 | 07-02 07:45:42.919 I/boot_progress_pms_scan_end( 1150): 12335 | events | 9337 | 51078 | 08-14 16:47:51.078 I/boot_progress_pms_scan_end( 1159): 13613
PMS ready状态开始 | 8630 | 42949 | 07-02 07:45:42.949 I/boot_progress_pms_ready( 1150): 12364 | events | 9397 | 51138 | 08-14 16:47:51.138 I/boot_progress_pms_ready( 1159): 13671
AMS ready状态开始 | 9810 | 44129 | 07-02 07:45:44.129 I/boot_progress_ams_ready( 1150): 13544 | events | 12507 | 54248 | 08-14 16:47:54.248 I/boot_progress_ams_ready( 1159): 16785
phone启动 | 9870 | 44189 | 07-02 07:45:44.189 I/am_proc_start( 1150): [0,1426,1001,com.android.phone,added application,com.android.phone] | events | 12587 | 54328 | 08-14 16:47:54.328 I/am_proc_start( 1159): [0,5383,1001,com.android.phone,added application,com.android.phone]
systemui启动 | 10060 | 44379 | 07-02 07:45:44.379 I/am_proc_start( 1150): [0,1507,10017,com.android.systemui,service,com.android.systemui/.SystemUIService] | events | 12727 | 54468 | 08-14 16:47:54.468 I/am_proc_start( 1159): [0,5451,10017,com.android.systemui,service,com.android.systemui/.SystemUIService]
usbui启动 | 10110 | 44429 | 07-02 07:45:44.429 I/am_proc_start( 1150): [0,1532,1000,com.android.usbui,service,com.android.usbui/.UsbUIService] | events | 12767 | 54508 | 08-14 16:47:54.508 I/am_proc_start( 1159): [0,5475,1000,com.android.usbui,service,com.android.usbui/.UsbUIService]
launcher启动 | 11130 | 45449 | 07-02 07:45:45.449 I/am_proc_start( 1150): [0,2033,10040,com.yulong.android.launcher3,activity,com.yulong.android.launcher3/.Launcher] | events | 13797 | 55538 | 08-14 16:47:55.538 I/am_proc_start( 1159): [0,5987,10041,com.yulong.android.launcher3,activity,com.yulong.android.launcher3/.Launcher]
AMS 启动完成 | 12130 | 46449 | 07-02 07:45:46.449 I/boot_progress_enable_screen( 1150): 15864 | events | 14897 | 56638 | 08-14 16:47:56.638 I/boot_progress_enable_screen( 1159): 19170
SurfaceFlinger关动画出keygurad | 14260 | 48579 | 07-02 07:45:48.579 I/SurfaceFlinger( 359): Boot is finished (14260 ms) | main | 9780 | 51708 | 08-14 16:47:51.708 I/SurfaceFlinger( 360): Boot is finished (10468 ms)
总耗时 | 17999 |  |  |  | 14054
内核系统日志同一时间点对标 |  |  | <6>[ 1.913200]@4 qcom,qpnp-rtc qpnp-rtc-ffffffc0c5691000: setting system clock to 2015-07-01 23:45:32 UTC (1435794332) | kmsg |  |  | <6>[ 1.745874]@0 qcom,qpnp-rtc qpnp-rtc-ffffffc0c5611400: setting system clock to 2015-07-05 21:00:57 UTC (1436130057)
initcall_debug printk.time=1两个参数，可以直接在fastboot下执行如下命令
fastboot oem param set initcall_debug
fastboot oem param set printk.time=1
fastboot oem param save
要想去除这两个参数，执行
fastboot oem param clear